### School of Advanced Technology

### Final Year Project

### Project Specification Report

Project Title: 构建类器官时序图像+药物文本多模态数据集

Student Name:Yuxin Zhang

Student ID: 2576576

Project field:生物信息、数据集开发、向量库性能测试

Supervisor:  Dechang Xu

Co-supervisor (if applicable):

- Project Description and Problem Statement

(Overall view of the project with proposed route to realization and answer why this project is important?)

Aims and Objectives

(What the project aims and objectives and how you are going to do it?)

目前Milvus等向量数据库都只用通用图片和文本做测试，没有专门的医学时序图像测试数据。缺少类器官显微图像搭配药物说明的专用测试素材，没法真实测出向量库在生物医药项目里的实际性能。

本项目先整理图文配对数据，制作标准测试数据集，最后对比多款向量数据库在这套医学数据上的检索速度与准确率。

意义：填补医疗领域专用测试集空白

- Project Plan: Tasks and Milestones (Gantt Chart)

(Indicate the tasks and milestones that should be achieved and their expected dates; e.g. Understanding of theory, designs of circuits, construction of circuits, software specifications, working demonstrations etc.)

1. 收集并整理类器官连续时序图片，配上对应的药物文字资料，清洗成干净的原始数据。

2. 把图文数据打包成标准测试包，划分好基础库与查询样本，适配Milvus测试格式。

3. 搭建统一测试环境，部署Milvus等至少3种向量数据库。

4. 测试检索耗时、准确度、内存占用，对比各个数据库的优劣。

5. 整理全部代码、数据集与测试结果。

3. 进度安排（甘特图）

1. 第1-3周：查阅文献，敲定整体方案

2. 第4-5周：收集图片和药物文本，完成数据整理

3. 第6-8周：标准化处理数据生成正式测试数据集

4. 第9-10周：部署多个向量数据库，搭建测试环境

5. 第11-13周：开展对比实验记录所有测试数据

6. 第14-16周：整理实验结果

- Project Deliverables

(Indicate what should be completed at the end of the project; e.g. This list should indicate

what will be presented / demonstrated at the final project demonstration.)

1. 图文配对的医学多模态测试数据集

2. 自动化测试Python代码

3. 多组向量数据库的对比测试报告

- Project Industrial Relevance

(Explain the relevance between this project and industrial’s needs)

这套专用医学测试集可以帮助企业选型数据库，测出产品在真实医疗数据下的性能，不用再依赖普通通用数据集，降低项目测试成本。

References

(The references will follow an IEEE style as shown in the examples.)

Books

[1] J. K. Author, “Title of chapter in the book,” in Title of His Published Book, xth ed.    City of Publisher, Country if not USA: Abbrev. of Publisher, year, ch. x, sec. x, pp. xxx–xxx.

Journals

[2] J. K. Author, “Name of paper,” Abbrev. Title of Periodical, vol. x, no. x, pp. xxx-xxx, Abbrev. of Month, year.

Conference Technical Articles

[3] J. K. Author, “Title of paper,” in Unabbreviated Name of Conf., City of Conf., Abbrev. State (if given), year, pp.xxx-xxx.

Online Sources

[4] J. K. Author, (year, Month. day). Title of web page [Online]. Available: URL http://www.../..../.../doc/text.